## Sheet1
User Story | Task | modules to code | priority | estimated time | status | assigned
user looks for individual skill (gab) | Use Case 6 (UC-6)
The end user would like to find someone to help with a youth project. They would like to narrow down the list of topics to a manageable list by searching a general topic list to get a narrowed down list. They would also like to search the list by alphabet for the first letter in case they are unable to find the topic by general list. | Code Keyword Search | Contorler request using keyword | 2 | 2 |  | gab
db search using keyword
show results page
| Code populate catagory list | db search using 'All' as keyword |  | 5
Contorler request using keyword
update category list
| Code populate Skills list | db search using 'All' as keyword
Contorler request using keyword
update skills list
| Code catagory list populate skills list | db search using keyword
Contorler request using keyword
update skills list
| Code Skill list search results | db search using keyword
Contorler request using keyword
show results page
Add/Edit User Skills (Cody) | Use Case 2 (UC-2)
An ADMIN will select the edit user skills button which takes them to the edit skills page. Once on the edit skills page the ADMIN will be given a series of questions such as a category drop down list for the skill category, and an additional information text field where the ADMIN can enter key words describing the skill. The bottom of the page will have a Submit button and a Back button. After the ADMIN has entered evrything in for the new skill the ADMIN will click submit which will then connect to the DB and make sure the values entered are acceptable. If the values are not acceptable the DB will send back an error page which will tell the ADMIN the problem with the values. If the values are accepted the DB will send back Confirmation page that tells the ADMIN the changes have been made to the user. | Code edit user skills button | Display edit skills page
| Code edit skills page | Category drop down list
Additional information text field
Submit and back buttons
| Code Error Page | Sent to edit skills page
| Code Confirmation Page | Sent to edit skills page
Edit Existing User (Jason) | Use Case 3 (UC-3)
A user would like to edit their own information, or an admin user would like to change an existing member record. The users log in and receive either a user or admin token. The user searches for a user, selects the user they want, update the desired information, and clicks save. The updated results are displayed. | Code button for SEARCH for user | display letters from alphabet
| Code select letter from alphabet | DB query for lastnames beginning with selected letter
display names beginning with letter
| Code selecting specific user from selected letter | db query for specific user
Controller request specific record
return user form with populated fields
| Code for updating existing member fields | db update record
Controller request to write to db
return updated fields
Add a new user (Mark) | Use Case 4 (UC-4)
The end user would like to add a new account to the system. The account may be a basic user or administrator account. | Code Add User button | display form window
| Code user information form | display window with all the fields. Refer to user, member, and address tables. all fields
set fields to blank
admin check box (default to uncheck)
Verify data entered into fields is valid
update user/admin field in db
| Code submit button | Verify data is correct
display content for user review
Code save button
Code edit button
Create db table for users | populate fields
User Table - User name, password, Account type/permission - needed for Admin, Member_ID(F_Key),
Member Table - Member_ID(P_Key), LName, FName, Phone, Email, Address_ID(F_Key), Skills(F_Key), Ward_ID(F_Key)
Address Table - Address_ID(P_Key), address, city, state, zipCode
Skills Table (lookup table)- Skill Category, Skill Name, Skill_ID(P-Key)
Geographic Information - Ward_Name, Ward_ID(P_Key), Stake_Name